## Instruction
Manual
Think before you act, do not remove formulas from the sheets ( check first )
First use
| Fill in the Project, Class and Team name in sheet Total | Vul de naam van het project en de klas en groep in op de tab "Totaal"
| Fill in the usernames for the students, remove unused names | Daarna eveneens de namen van de 4 studenten
Need more activity lines in some week |  | Meer activiteitregels nodig in een week?
| Copy the last line and insert it before the total line | Maak een kopie van de laatste activiteitregel en voeg deze in voor de totaalregel

## Total
Time registration |  | Students | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Total
Project : | Client On Board | Anastasiia Khylyk | 3.5 | 4.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 9.5
|  | Anh Nguyen | 3.5 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 13.5
Class & Team | DHI2V.So - Ctrl+alt+elite | Krisztian Kozari | 4.5 | 5.5 | 6.5 | 0 | 0 | 0 | 0 | 0 | 16.5
|  | Andre Nguyễn | 4.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5
|  | David Maddin | 3 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5
|  | Krzysztof Jarosz | 3 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5
|  | Radin Soleymani | 6.5 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25
|  | Student-8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Student-9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Student-10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Weektotal | 28.5 | 33.75 | 14 | 0 | 0 | 0 | 0 | 0
|  | Sprinttotal |  | 62.25 |  | 14 |  | 0 |  | 0
|  | Hours to burn | 931.5 | 897.75 | 883.75 | 883.75 | 883.75 | 883.75 | 883.75 | 883.75
Available hours per week : | 120 | Total Hours available | 960 | 840 | 720 | 600 | 480 | 360 | 240 | 120

## Week 1
Week 1 | Hours TOTAL
Anastasiia Khylyk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Creating issue boards, description and formatting of gitlab issues | 0.5 |  |  |  |  | 1 | 1.5
Writing questions to client |  | 0.5 |  |  |  |  | 0.5
Initial framework research |  | 0.5 |  |  |  |  | 0.5
Planning meeting 14.11 |  |  | 1 |  |  |  | 1
Total | 0.5 | 1 | 1 | 0 | 0 | 1 | 3.5
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Writing questions to client |  |  | 0.5 |  |  |  | 0.5
Fixing questions sheet | [5 empty] | 2 | 2
Change log creation for questions | [5 empty] | 1 | 1
0
0
Total | 0 | 0 | 0.5 | 0 | 0 | 3 | 3.5
Krisztian Kozari | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | 2 | [5 empty] | 2
Initial infrastructure setup | 0.5 | [5 empty] | 0.5
Git setup and management |  | 1 |  |  |  |  | 1
Framework research |  |  |  | 0.5 |  |  | 0.5
Writing client questions |  |  |  | 0.5 |  |  | 0.5
Total | 2.5 | 1 | 0 | 1 | 0 | 0 | 4.5
Andre Nguyễn | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Research client's need | 1 | 1 |  |  |  |  | 2
Questions for the client |  |  | 1 | 0.5 |  |  | 1.5
Work on document |  |  |  |  | 0.5 | 0.5 | 1
0
0
Total | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 4.5
David Maddin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Writing questions to client | [5 empty] | 0.5 | 0.5
Repo Files Setup | 0.5 | [5 empty] | 0.5
Functional Design v1.0 | 2 | [5 empty] | 2
0
0
Total | 2.5 | 0 | 0 | 0 | 0 | 0.5 | 3
Krzysztof Jarosz | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Planning meeting 14.11 |  |  | 1 |  |  |  | 1
Writing questions to client |  | 1 |  |  |  |  | 1
Client meeting preparations and planning |  |  |  |  | 1 |  | 1
0
0
Total | 0 | 1 | 1 | 0 | 1 | 0 | 3
Radin Soleymani | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | 2 | [5 empty] | 2
Write code of conduct |  | 0.5 |  |  |  |  | 0.5
Write Definition of Done document |  |  |  | 1
Write code quality document |  |  |  | 1 |  |  | 1
Create an early draft of all questions that need to be discussed with the client |  | 1 |  |  |  |  | 1
create a manual document for sprint 0 for kick off | 0.5
create a project goals, deliverables, and expectations document for kick off | 0.5 | [5 empty] | 0.5
Total | 3 | 1.5 | 0 | 2 | 0 | 0 | 6.5

## Week 2
Week 2 | Hours TOTAL
Anastasiia Khylyk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
#20 Format client's answers into client communication log |  |  |  |  | 0.5 | 1 | 1.5
Planning meeting agenda for Monday | [5 empty] | 1 | 1
Researching frameworks after meeting the client | [5 empty] | 0.5 | 0.5
Drafting backlog items for Sprint 1 | [5 empty] | 1.5 | 1.5
0
Total | 0 | 0 | 0 | 0 | 0.5 | 4 | 4.5
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Audio API research |  |  |  | 1 |  |  | 1
Text-to-Speech API |  |  |  |  | 1 |  | 1
Test code for audio APIs | [5 empty] | 2 | 2
0
0
Total | 0 | 0 | 0 | 1 | 1 | 2 | 4
Krisztian Kozari | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Git management | [5 empty] | 0.5 | 0.5
Framework research post client meeting |  |  |  |  | 1 | 2 | 3
shadcn research (Component library) |  |  | 2 |  |  |  | 2
0
0
Total | 0 | 0 | 2 | 0 | 1 | 2.5 | 5.5
Andre Nguyễn | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Write project plan | 1 | 1 |  |  |  |  | 2
API research |  | 0.5 |  |  |  |  | 0.5
Work on wireframes |  |  | 1 | 1 |  |  | 2
Research libraries for Svelte |  |  |  |  | 0.5 |  | 0.5
Solutions post meeting | [5 empty] | 1 | 1
Total | 1 | 1.5 | 1 | 1 | 0.5 | 1 | 6
David Maddin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Functional Design v1.0 |  | 0.5 |  |  |  |  | 0.5
Meeting Planning |  |  | 2 |  |  |  | 2
Functional Design v2.0 | [5 empty] | 2 | 2
0
0
Total | 0 | 0.5 | 2 | 0 | 0 | 2 | 4.5
Krzysztof Jarosz | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
solution research post meeting | [5 empty] | 3 | 3
Planning meeting agenda for Monday |  |  |  |  | 1 |  | 1
creating design concepts | 1 |  | 0.5 |  |  |  | 1.5
0
0
Total | 1 | 0 | 0.5 | 0 | 1 | 3 | 5.5
Radin Soleymani | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Write Definition of Done document |  | 1 |  |  |  |  | 1
Make Technical design markdown template |  | 0.25 |  |  |  |  | 0.25
Make Client comminucation log markdown template. |  | 0.25 |  |  |  |  | 0.25
Drafting backlog items for Sprint 1 | [5 empty] | 1.5 | 1.5
Post-client meeting assembly |  |  |  | 0.75 |  |  | 0.75
Total | 0 | 1.5 | 0 | 0.75 | 0 | 1.5 | 3.75

## Week 3
Week 3 | Hours TOTAL
Anastasiia Khylyk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Writing Sprint 1 vision for client | 0.5 | [5 empty] | 0.5
Drafting issues for Sprint 1 |  | 1 |  |  |  |  | 1
0
0
0
Total | 0.5 | 1 | 0 | 0 | 0 | 0 | 1.5
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
DeepSpeech | 4 | [5 empty] | 4
Vosk | 2 | [5 empty] | 2
0
0
0
Total | 6 | 0 | 0 | 0 | 0 | 0 | 6
Krisztian Kozari | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Speech recognition software research | 1 | [5 empty] | 1
Whisper ai trial and research | 3 | [5 empty] | 3
Frontend setup |  | 2 |  |  |  |  | 2
Git management |  | 0.5 |  |  |  |  | 0.5
0
Total | 4 | 2.5 | 0 | 0 | 0 | 0 | 6.5
Andre Nguyễn | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
David Maddin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krzysztof Jarosz | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radin Soleymani | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-8 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-9 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-10 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week 4
Week 4 | Hours TOTAL
Anastasiia Khylyk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krisztian Kozari | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Andre Nguyễn | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
David Maddin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krzysztof Jarosz | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radin Soleymani | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-8 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-9 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-10 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week 5
Week 5 | Hours TOTAL
Anastasiia Khylyk | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krisztian Kozari | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Andre Nguyễn | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
David Maddin | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krzysztof Jarosz | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radin Soleymani | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-8 | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-9 | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-10 | Uren
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week 6
Week 6 | Hours TOTAL
Anastasiia Khylyk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krisztian Kozari | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Andre Nguyễn | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
David Maddin | Hours
User story / task description |  | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krzysztof Jarosz | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radin Soleymani | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-8 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-9 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-10 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week 7
Week 7 | Hours TOTAL
Anastasiia Khylyk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krisztian Kozari | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Andre Nguyễn | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
David Maddin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krzysztof Jarosz | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radin Soleymani | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-8 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-9 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-10 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Week 8
Week 8 | Hours TOTAL
Anastasiia Khylyk | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anh Nguyen | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krisztian Kozari | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Andre Nguyễn | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
David Maddin | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Krzysztof Jarosz | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radin Soleymani | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-8 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-9 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0
Student-10 | Hours
User story / task description | Ma | Di | Wo | Do | Vr | Za/Zo | Total
Kickoff | [6 empty] | 0
0
0
0
0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0